## Planilha1
Total time spent |  |  |  | 21:10
Day | Start | End | Description | Total
2021-05-16 | 0:00 | 0:41 | Solution kick off. Trello creation and tasks organization. | 0:41
2021-05-16 | 15:40 | 17:30 | Project structure. Entities creation. | 1:50
2021-05-16 | 18:20 | 19:00 | Architecture design | 0:40
2021-05-16 | 19:00 | 22:00 | Repositories and mongo configuration | 3:00
2021-05-16 | 22:00 | 23:30 | Added swagger and create game endpoint | 1:30
2021-05-17 | 0:20 | 0:55 | Game basic validation. Started visit cell endpoint | 0:35
2021-05-17 | 23:20 | 23:59 | Visit cell endpoint. Calculate cell value on game creation. | 0:39
2021-05-18 | 0:00 | 1:05 | Finished visit cell endpoint functionally. | 1:05
2021-05-18 | 22:00 | 22:30 | NodeJS structure for api client lib. | 0:30
2021-05-18 | 23:35 | 23:59 | NodeJS structure for api client lib. | 0:24
2021-05-19 | 0:00 | 0:40 | NodeJS structure for api client lib. | 0:40
2021-05-19 | 21:35 | 22:43 | Methods to create a game and visit a cell on client api. | 1:08
2021-05-19 | 22:43 | 23:20 | Endpoint to flag a cell. | 0:37
2021-05-19 | 23:25 | 23:43 | Endpoints to pause/resume a game. | 0:18
2021-05-20 | 0:24 | 1:08 | Game time tracking. | 0:44
2021-05-20 | 1:08 | 1:40 | Methods to pause, resume, get a game and method to flag a cell on client api. | 0:32
2021-05-22 | 11:10 | 13:36 | Endpoints to create user and login. | 2:26
2021-05-22 | 15:00 | 17:00 | Added swagger documentation and authorization on API. | 2:00
2021-05-22 | 17:00 | 17:40 | Added methods to create user and login on client api. | 0:40
2021-05-23 | 0:10 | 1:21 | Deploy configuration. | 1:11
0:00
0:00
0:00
0:00